## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date | Existing Operation Maintenance Date | Proposed Change Date for Operation Maintenance | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | AE(T) Margalla | 132Kv Wah-83 controlling 132/66KV 31.5/140MVA Power Transformer T-3 at 132KV GSS New Wah |  |  | 06-02-2025 to 15.03.2025 (Contineous) |  |  | 06.02.2025 0900Hrs | 15.03.2025 0900Hrs | For dismentling the existing 132KV Transformer Bay & 66KV Line Bay Haripure-Havelian to Spare this line bay for 132KV T/Line New wah to Bahtarmore | No Area will be affected, 66Kv GSS Haripure will be fed from Havelian (PESCO)
3 | IESCO | IBD | XEN-II | G-11 | H-11 | Bala Road | 72723 | 11.03.2025 15.03.2025 |  |  | 08.00 AM | 11.00 AM | Shifting of HT/LT line Safety Hazards Works/LV Proposals Islamabad | G-12 Chowk
4 | IESCO | IBD | XEN-I | F-11 | D-12 | Railway Road | 104004 | 17.03.2025 | [5 empty] | Draikh Moori Chowk
5 | IESCO | IBD | XEN-I | Tarlai | Taramri | Sharifabad | 105521 | 18.03.2025 20.03.2025 24.03.2025 | [5 empty] | Sharifabad
3 | IESCO | Jhelum | Jhelum-I | S.A.Gir | Rajjar | Chapran | 47011 | 14.03.2025 |  |  | 0800 Hrs | 1100 Hrs | Execution of LV work Khohar & Qazi Baqar | Chaparn, Aurang Abad
4 | IESCO | Jhelum | Jhelum-I | Rajjar | Rajjar | Mandi Bhalwal | 47010 | 11.0320.25 | [5 empty] | Mandi Bhalwal,
5 | IESCO | Jhelum | Jhelum-I | Rajjar | Rajjar | Bolani | 47006 | 13.03.2025 | [5 empty] | Bolani etc
6 | IESCO | Jhelum | Jhelum-I | Rajjar | Rajjar | Shakreela | 47003 | 12.03.2025 | [5 empty] | Shakreela,
1 | IESCO | Attock | Taxila | Margalla | 132 KV GSS Bahtar More New City | Dharik | 112006 | 06.03.2024, 11.03.2025, 13.03.2025 |  |  | 10:00 Hours | 12:00 Hours | Shifting of HT Kline Dhraik Feeder Work at ROW location. | Village Dhraik and Surrounding.
1 | IESCO | RWP | Cantt | Civil Line | Chaklala | RIC | 2534 | 08-03-2025 15-03-2025 |  |  | 07:00 | 12:00 | Tentative D/N for External Electrification of Takbeer 1 Project ( A Project of CWO) Kot Jabbi Rwp | Civil Line
2 | IESCO | RWP | Satellite Town | Chandni Chowk | Chaklala | Benazir Bhutto | 2537 |  |  |  | 07:00 | 12:00 |  | Chandni Chowk
3 | IESCO | RWP | Cantt | Chaklala | Chaklala | Gracy Line | 2533 |  |  |  | 07:00 | 12:00 |  | Gracy Line
4 | IESCO | RWP | Satellite Town | Gulzar e Qaid | Chaklala | Sector-IV | 2536 | 10-03-2025 13-03-2025 17-03-2025 20-03-2025 24-03-2025 27-03-2025 |  |  | 07:00 | 12:00 | Tentative D/N for External Electrification of Takbeer 1 Project ( A Project of CWO) Kot Jabbi Rwp | Sector-IV
5 | IESCO | RWP | Cantt | Chaklala | Chaklala | Rehmatabad-I | 2519 |  |  |  | 07:00 | 12:00 |  | Rehmatabad-I
6 | IESCO | RWP | Cantt | Chaklala | Chaklala | Chaklala | 2503 |  |  |  | 07:00 | 12:00 |  | Chaklala
7 | IESCO | RWP | Satellite Town | Gulzar e Qaid | Chaklala | Airport Society | 2526 |  |  |  | 07:00 | 12:00 |  | Airport Society
8 | IESCO | IBD | No.I | Tarlai | Tramri | Kund Rajgan | 105522 | 06-03-2025 11-03-2025 18-03-2025 25-03-2025 |  |  | 07:00 | 11:00 | Provision of Electricity Connection IRO King Hammad University of Nursing and Allied Science Park Road ICT. | Kund Rajgan
9 | IESCO | IBD | NO.I | Tarlai | Tarmari | Chatta Bakhtwar | 105507 |  |  |  | 07:00 | 11:00 |  | Chatta Bakhtwar
10 | IESCO | IBD | NO.I | Tarlai | Tarmari | Tarmari | 105503 |  |  |  | 07:00 | 11:00 |  | Tarmari
11 | IESCO | IBD | Bhara Kauh | Bhara Kauh Urban | Tarmari | Rehara | 105511 |  |  |  | 07:00 | 11:00 |  | Rehara
13 | IESCO | Attock | Taxila | Taxila | HMC Taxila | Salar Gah | 21223 | 20-03-2025 |  |  | 07:00 | 11:00 | Net for Railway Corssing | Salar Gah
14 | IESCO | Attock | Taxila | Taxila | HMC Taxila | Ghuri | 21219 |  |  |  | 07:00 | 11:00 |  | Usman Khatar
15 | IESCO | Attock | Taxila | Taxila | 132KV Taxila | Eng Universty | 21201 | 12-03-2025 |  |  | 07:00 | 11:00 | Net for Railway Corssing | Eng Universty
16 | IESCO | Attock | Taxila | Taxila |  | HIT | - |  |  |  | 07:00 | 11:00 |  | HIT
17 | IESCO | Attock | Taxila | Taxila |  | Musem | 21214 |  |  |  | 07:00 | 11:00 |  | Rehber Colony
18 | IESCO | Attock | Taxila | Taxila | 132KV Taxila | Nisar Shaheed | 21220 | 26-03-2025 |  |  | 07:00 | 11:00 |  | Dibia
19 | IESCO | Attock | Taxila | Taxila |  | Margalla | 21211 |  |  |  | 07:00 | 11:00 |  | Margalla
20 | IESCO | Attock | Taxila | Taxila | 220KV Sangjani | D-18 | 81005 | 06-03-2025 12-03-2025 |  |  | 07:00 | 11:00 | Shifting of HT Line near Sangjani Grid | D-18
21 | IESCO | Attock | Taxila | Taxila | 220KV Sangjani | D-17 | 81010 |  |  |  | 07:00 | 11:00 |  | D-17
28 | IESCO | Attock | Taxila | Taxila | 132KV B17 | Saray Kharboza | 121802 | 06-03-2025 25-03-2025 |  |  | 07:00 | 11:00 | Shifting of HT Line near Sangjani Grid & Moh: Usmani & LV | Saray Kharboza
29 | IESCO | Attock | Taxila | Taxila | 220KV Sangjani | Shah Allah Ditta | 81011 | 06-03-2025 12-03-2025 |  |  | 07:00 | 11:00 | Shifting of HT Line near Sangjani Grid Hazard Work Dk Paracha | Shah Allah Ditta Dk Abbasi
31 | IESCO | Attock | Taxila | Hassan Abdal | 132KV New Wah | Hussain Abad | 14627 | 06-03-2025 11-03-2025 20-03-2025 |  |  | 07:00 | 11:00 | Re-Conductoring of 11KV Feeders | Hussain Abad
32 | IESCO | Attock | Taxila | Mora Chowk | 132KV New Wah | Munir Abad | 14628 |  |  |  | 07:00 | 11:00 |  | Munir Abad
33 | IESCO | Attock | Taxila | Hassan Abdal | 132KV New Wah | Ahmed Nagar | 14632 |  |  |  | 07:00 | 11:00 |  | Ahmed Nagar
34 | IESCO | Attock | Taxila | Hassan Abdal | 132KV New Wah | Col: Sher Khan | 14621 |  |  |  | 07:00 | 11:00 |  | Village Wah
35 | IESCO | Attock | Taxila | Wah Cantt | 132KV New Wah | Lala Zar | 14607 |  |  |  | 07:00 | 11:00 |  | Lala Zar
37 | IESCO | Cantt | Cantt | Sowan | 132KV Sowan | Mehboob Shaheed | 87418 | 12.03.2025 17.03.2025 19.03.2025 24.03.2025 26.03.2025 | - |  | 07:00 | 11:00 | For reconductoring of Fauji Foundation Feeder & shifting of HT/ LT Lines Deposit Work Potohar Avenue | Chiriten Colony & Surrounding area
38 | IESCO | Cantt | Cantt | Morgah | 132KV Sowan | Park View | 87410 |  | - |  | 07:00 | 11:00 |  | Morgah, Park View and Surrounding area.
39 | IESCO | Cantt | Cantt | Morgah | 132KV Sowan | Pindi Board | 87415 |  | - |  | 07:00 | 11:00 |  | BISE & Surrounding area.
40 | IESCO | Cantt | Cantt | Korang | 132KV Sowan | Jail Park-1 | 87407 |  | - |  | 07:00 | 11:00 |  | Boastan Road Car Chowk & Surrounding area
41 | IESCO | Cantt | Cantt | Korang | 132KV Sowan | Car Chowk | 87414 |  | - |  | 07:00 | 11:00 |  | Car Chowk & Surrounding
42 | IESCO | Cantt | Cantt | Morgah | 132KV Sowan | Ex Lawyer | 87416 |  | - |  | 07:00 | 11:00 |  | EX Lawyer
43 | IESCO | Cantt | Cantt | Morgah | 132KV Sowan | AOWHS | 87402 |  | - |  | 07:00 | 11:00 |  | AOWHS & Surrounding area
44 | IESCO | Cantt | Cantt | Morgah | 132KV Sowan | Morgah | 87406 | 10.03.2025 12.03.2025 | - |  | 07:00 | 11:00 |  | Morgah and Surrounding .
45 | IESCO | Cantt | Cantt | Morgah | 132KV Sowan | Pindi Board | 87415 |  | - |  | 07:00 | 11:00 |  | BISE & Surrounding area.
46 | IESCO | Cantt | Cantt | Morgah | 132KV Sowan | Park View | 87410 |  | - |  | 07:00 | 11:00 |  | Morgah, Park View and Surrounding area.
50 | IESCO | Cantt | Rawat | Rawat | 132KV Old Rawat | RCCI-I | 17715 | 09.03.2025 16.03.2025 23.03.2025 30.03.2025 | - |  | 07:00 | 11:00 | For shifting of load to newly constructed RCCI Grid Station | RCCI & sorrounding area
51 | IESCO | Cantt | Rawat | Rawat | 132KV Old Rawat | RCCI-III | 17726 |  | - |  | 07:00 | 11:00 |  | RCCI & sorrounding area
52 | IESCO | Cantt | Rawat | Rawat | 132KV Old Rawat | RCCI-IV | 17730 |  | - |  | 07:00 | 11:00 |  | RCCI & sorrounding area
53 | IESCO | Cantt | Korang | Korang | 132KV GSS NPF | Doctor Town | 90016 | 06.03.2025 13.03.2025 18.03.2025 | - |  | 07:00 | 11:00 | LT Line O/H to U-G | Doctor Town
54 | IESCO | Cantt | Korang | Saddar | 132KV GSS MES | Mall Road | 107602 | 20.03.2025 25.03.2025 | - |  | 07:00 | 11:00 | Victoria Plaza' | Mall Road & sorrounding area
55 | IESCO | Cantt | Cantt | Wadala | 132KV Old Rawat | Basali | 17728 | 08.03.2025 11.03.2025 15.03.2025 18.03.2025 24.03.2025 27.03.2025 | - |  | 07:00 | 11:00 | Shifting of HT / LT line IRO Rawalpindi Ring Road Project | Basali & surrounding area
56 | IESCO | Cantt | Cantt | Wadala | 500KV New Rawat | Jhata Hatyal | 64503 |  | - |  | 07:00 | 11:00 |  | Jhata hatyal & Surrounding areas
57 | IESCO | Cantt | Cantt | Wadala | 132KV Old Rawat | New kalyam | 17721 |  | - |  | 07:00 | 11:00 |  | New Kalyam & Surrounding areas
58 | IESCO | Cantt | Cantt | Wadala | 500KV New Rawat | Industrial | 64502 |  | - |  | 07:00 | 11:00 |  | Industrial & Surrounding areas
59 | IESCO | Cantt | Cantt | Mandra | 500KV New Rawat | Gumti | 64512 |  | - |  | 07:00 | 11:00 |  | Gumti & Surrounding areas
60 | IESCO | Cantt | Cantt | Wadala | 132KV Old Rawat | Old Kalyam | 17710 |  | - |  | 07:00 | 11:00 |  | Kalyam & surrounding areas
61 | IESCO | Cantt | Cantt | Chak Bali | 500KV New Rawat | Bhal | 64507 |  | - |  | 07:00 | 11:00 |  | Bahl & surounding areas
62 | IESCO | Cantt | Cantt | Dhaimial | 132KV Ranyal | Moorat | 120405 |  | - |  | 07:00 | 11:00 |  | Moorat & Surrounding areas
63 | IESCO | Cantt | Cantt | Adiala | 132KV Adiala | Khasala | 109108 |  | - |  | 07:00 | 11:00 |  | Khasala & Surrounding areas
64 | IESCO | Cantt | Cantt | Adiala | 500KV Rawat | Jarar Camp | 64510 |  | - |  | 07:00 | 11:00 |  | Jarrar Camp
65 | IESCO | Cantt | T/Abad | Q.A Colony | 132KV Kamalabad | Shah Jevan | 001021 | 13.03.2025 | - |  | 07:00 | 11:00 | For Instalation of Poles of IIKV Maj Riaz Manzoor Feeder EMA enenmationg from 132KV Kamalabad Grid Station Work Order No. 2K24-462, ELR-HT-13 | Cirection colony, shah jeven colony, habib colony ect.
66 | IESCO | Cantt | T/Abad | Q.A Colony | 132KV Kamalabad | Quaid e Azam Colony | 001003 |  | - |  | 07:00 | 11:00 |  | Q.A Cly & Surrounding areas
67 | IESCO | Cantt | T/Abad | Dhamial | 132KV Kamalabad | Dhamial | 001014 |  | - |  | 07:00 | 11:00 |  | Dhamial Village & Surrounding areas
68 | IESCO | Cantt | T/Abad | Q.A Colony | 132KV Kamalabad | UC Lakhan | 001015 | 13.03.2025 | - |  | 07:00 | 11:00 | For Instalation of Poles of IIKV Maj Riaz Manzoor Feeder EMA enenmationg from 132KV Kamalabad Grid Station Work Order No. 2K24-462, ELR-HT-13 | Girja Road, Chak Jalal Din, Chirtian Cly, Malik Abad.
69 | IESCO | Cantt | T/Abad | Q.A Colony | 132KV Kamalabad | Gulshan e Saeed | 001024 |  | - |  | 07:00 | 11:00 |  | Thallian ,Dhoke Sama.Pelo .ect
70 | IESCO | Cantt | T/Abad | R.A Bazar | 132KV Kamalabad | Cantt | 001002 |  | - |  | 07:00 | 11:00 |  | Narozabad, Harley Street Lane No.1 to 10, Tahli Mohri, GHQ, CMH, CSD.
71 | IESCO | Cantt | T/Abad | R.A Bazar | 132KV Kamalabad | Qasim Base | 001023 |  | - |  | 07:00 | 11:00 |  | Independent 11KV Feeder
72 | IESCO | Cantt | T/Abad | TariqAbad | 132KV Kamalabad | Maj Riaz Manzoor | 001017 |  | - |  | 07:00 | 11:00 |  | Maj Riaz Manzoor Road & Surrounding
73 | IESCO | Cantt | T/Abad | TariqAbad | 132KV Kamalabad | Tulsa Road |  |  | - |  | 07:00 | 11:00 |  | Tulsa Road & Surrounding
74 | IESCO | Cantt | T/Abad | TariqAbad | 132KV Kamalabad | Lalazar | 001005 |  | - |  | 07:00 | 11:00 |  | lazar Colony & Surrounding areas
75 | IESCO | Cantt | T/Abad | R.A Bazar | 132KV Kamalabad | Jhawara | 001016 |  | - |  | 07:00 | 11:00 |  | Jhwar & Surrounding area
76 | IESCO | Cantt | T/Abad | TariqAbad | 132KV Kamalabad | Lalkurti | 001004 |  | - |  | 07:00 | 11:00 |  | Lalkurti & Surrounding areas
77 | IESCO | Cantt | Tariqabad | Adyala | 132KV Adyala | Defence Road | 109113 | 06.03.2025 08.03.2025 19.03.2025 | - |  | 07:00 | 12:00 | For dismantling/ shifting of poles at Khawaja Corporation Chowk Adyala Road Rawalpindi | Defence Road & sorrounding area | For Safety Purpose
78 | IESCO | Cantt | Tariqabad | Tariqabad | 132KV Adyala | Hamayoun 1 | 109111 |  | - |  | 07:00 | 12:00 |  | Humayoun Road & sorrounding area
79 | IESCO | Cantt | Tariqabad | Adyala | 132KV Adyala | Rose Lane | 109112 |  | - |  | 07:00 | 12:00 |  | Rose Lane & sorrounding area
80 | IESCO | Cantt | Tariqabad |  | 132KV Adyala | Adyala | 109106 |  | - |  | 07:00 | 12:00 |  | Adyala & sorrounding area
81 | IESCO | Cantt | Tariqabad |  | 132KV Adyala | Kalyal | 109101 |  | - |  | 07:00 | 12:00 |  | Kalyal & sorrounding area
82 | IESCO | Cantt | Tariqabad | Tariqabad | 132KV Chaklala | Humayoun Road | 002525 |  | - |  | 07:00 | 12:00 |  | Humayoun Road & sorrounding area
83 | IESCO | City | Westridge | Tarnol | KTM | Modern Floor Mill | 8603 | 08.03.2025 10.03.2025 15.03.2025 |  |  | 07:00 | 11:00 | Reconductoring of Shams Colony feeder | Modern Floor Mill
84 | IESCO | City | Westridge | Tarnol | KTM | Shams Cly | 8626 |  |  |  | 07:00 | 11:00 |  | H-13 & surroundings
85 | IESCO | City | Westridge | Tarnol | KTM | Quaid Azam Hospital | 8624 |  |  |  | 07:00 | 11:00 |  | Quaid Azam Hospital & surroundings
86 | IESCO | City | City | Pirwadhai | KTM | Raja Abad | 8619 |  |  |  | 07:00 | 11:00 |  | Pak Floor Mill , British Home, Gulshan e Safeer, CTTI , Gulistan e Paker, Sulman Abad, Qasim Abad.
87 | IESCO | City | Westridge | Tarnol | KTM | Zarkoon Heights | 8628 |  |  |  | 07:00 | 11:00 |  | Zarkoon Heights & surroundings
88 | IESCO | City | Westridge | Tarnol | KTM | P&T Wani | 8610 |  |  |  | 07:00 | 11:00 |  | Jhangi Syedan, Haidery Chowk & surrounding
89 | IESCO | City | City | Pirwadhai | KTM | Westridge | 8613 |  |  |  | 07:00 | 11:00 |  | Muhammad Abad, Chur Harpal , Ali Abad, China Chowk
90 | IESCO | City | Westridge | Tarnol | KTM | Golra | 8605 |  |  |  | 07:00 | 11:00 |  | Naseer abad, Awan Town & surroundings
91 | IESCO | City | Westridge | Seham | KTM | Chakra | 8604 | 06.03.2025 20.03.2025 22.03.2025 27.03.2025 |  |  | 07:00 | 11:00 | Reconductoring of Seham Feeder | ChishtiaAbad, Mohammadi Colony, Dk. Sada Road
92 | IESCO | City | Westridge | Seham | KTM | Seham | 8618 |  |  |  | 07:00 | 11:00 |  | Usmania Colony, Qadria Colony, Farooq Abad
93 | IESCO | City | Westridge | Seham | KTM | Range Road | 8627 |  |  |  | 07:00 | 11:00 |  | Mukarram Town, Mohallah Rajputan, Range Road
94 | IESCO | City | Westridge | Tarnol | KTM | Modern Floor Mill | 8603 |  |  |  | 07:00 | 11:00 |  | Modern Floor Mill
95 | IESCO | City | Westridge | Westridge | KTM | Millatabad | 8616 |  |  |  | 07:00 | 11:00 |  | Misrial Road,Ilyas Colony,Lane No.1,2,3 and Srounding Areas
96 | IESCO | City | Westridge | Tarnol | KTM | KTM | 8609 |  |  |  | 07:00 | 11:00
97 | IESCO | City | Westridge | Westridge | KTM | Peshawar Road | 8612 |  |  |  | 07:00 | 11:00 |  | Peshawar Road, Lane 4 to 7, Mehboob Lane Fazalabad, Pirwadhai More
98 | IESCO | City | Westridge | Tarnol | KTM | Quaid Azam Hospital | 8624 |  |  |  | 07:00 | 11:00 |  | Quaid Azam Hospital & surroundings
99 | IESCO | City | Westridge | Tarnol | KTM | Modern Floor Mill | 8603 | 13.03.2025 24.03.2025 29.03.2025 |  |  | 07:00 | 11:00 | Reconductoring of Shams Colony feeder | Modern Floor Mill
100 | IESCO | City | Westridge | Tarnol | KTM | Shams Cly | 8626 |  |  |  | 07:00 | 11:00 |  | H-13 & SURROUNDING
101 | IESCO | City | Westridge | Misrial | Pirwadhai | Madina Cly | 43334 | 11.03.2025 17.03.2025 |  |  | 07:00 | 11:00 | For LV work at Capt.Toor Street Range Road | Madina Cly & surroundings
102 | IESCO | City | Westridge | Seham | KTM | Range Road | 8627 |  |  |  | 07:00 | 11:00 |  | Mukarram Town, Mohallah Rajputan, Range Road
103 | IESCO | City | Westridge | Kamalabad | I-16 | Ameer Hamza | 104616 |  |  |  | 07:00 | 11:00 |  | Dk. Gujran, Ameer Hamza cly, Chakra Raod, Bait e Sada Colony, Misrial Road.
104 | IESCO | City | Westridge | Kamalabad | Kamalabad | Radio Pak-I | 1006 | 12.03.2025 18.03.2025 26.03.2025 |  |  | 07:00 | 11:00 | Safety Hazard Work at Muhammadi Masjid | Baraf Khana, Chamanabad, Madina Colony, Misrial Road
105 | IESCO | City | Westridge | Seham | I-16 | Noon | 104603 | 31.03.2025 |  |  | 07:00 | 11:00 | For LV work at NR.Saeed Toota House. | Noon, Dk.Makhan, Lakhu, Jatal
106 | IESCO | City | Westridge | Seham | KTM | Chakra | 8604 |  |  |  | 07:00 | 11:00 |  | ChishtiaAbad, Mohammadi Colony, Dk. Sada Road
107 | IESCO | Cantt | Rawat | Rawat | 132KV Gangal | Japan Road | 110901 | 06.03.2025 10.03.2025 12.03.2025 20.03.2025 25.03.2025 27.03.2025 |  |  | 07:00 | 11:00 | For erection of poles/ stringing of HT Conductor iro Bifurcation of 11KV Sihala & Reconductoring of 11KV Japan Road Feeder | Japan Road & sorrounding area
108 | IESCO | Cantt | Rawat | Rawat | 132KV Gangal | Jinnah-I | 110906 |  |  |  | 07:00 | 11:00 | For safety Purpose | Jinnah Garden Society & sorrounding area
109 | IESCO | Cantt | Rawat | Rawat | 132KV Gangal | Jinnah-II | 110907 |  |  |  | 07:00 | 11:00 |  | Jinnah Garden Society & sorrounding area
110 | IESCO | Cantt | Rawat | Kallar Syedan | 132KV Kallar | Kallar City | 098104 | 11.03.2025 16.03.2025 22.03.2025 25.03.2025 29.03.2025 | - |  | 07:00 | 11:00 | For area planning of 11KV Kallar City & 11KV Kallar Syedan Feeder along with shifting of 11KV Kallar Syedan Feeder from 132KV Old Rawat GSS to 132KV Kallar Syedan GSS under ELR Head | Kallar Syedan & sorrounding area
111 | IESCO | Cantt | Rawat | Kallar Syedan | 132KV Kallar | Doberan | 098106 |  | - |  | 07:00 | 11:00 |  | Doberan & sorrounding area
2 | IESCO | City | Satellite Town | Sadiqabad | Satellite Town | Affandi Colony | 095808 | 10/03/2025 13/03/2025 |  |  |  |  | Stringing work IRO LV work Nr.Delhi Optical Sadiqabad (2k23-431-03-65) | S/Abad,MuslimTown,Affandi Cly & suroundings
1 | IESCO | IBD | Div-1 | Nilore | 132/220kv G/S B/Khu | Athal | 89217 | 10.03.2025 13.03.2025 17.03.2025 20.03.2025 24.03.2025 26.03.2025 |  |  | 07:00 | 11:00 | Bifurcation of Shah Pur Feeder /Strinning of HT line in R/O External Electrification of Park View City Housing Society | Athal Road, Tumair, Athal vill.
2 | IESCO | IBD | B/Khu | B/Khu (R) | 132/220 KV G/S B/Khu | Treat | 89203 |  |  |  | 07:00 | 11:00 |  | Treat and Surrounding Area
3 | IESCO | IBD | B/Khu | B/Khu (U) | 132/220 KV G/S B/Khu | T&T | 89204 |  |  |  | 07:00 | 11:00 |  | Mango Town 17 Meel and Surrounding Area
4 | IESCO | IBD | B/Khu | B/Khu (U) | 132/220 KV G/S B/Khu | B/ Khu-II | 89219 |  |  |  | 07:00 | 11:00 |  | Madina Town, Nain Sukh,and Surrounding Area
5 | IESCO | IBD | B/Khu | B/Khu (U) | 132/220 KV G/S B/Khu | B/ Khu-I | 89201 |  |  |  | 07:00 | 11:00 |  | Bhara Kahu Bazar, Sanjalian and Surrounding Area
6 | IESCO | IBD | B/Khu | B/Khu (U) | 132/220KV G/S B/Khu | NIH | 89210 |  |  |  | 07:00 | 11:00 |  | jillani,DK Mohri Lake View LVL
7 | IESCO | IBD | B/Khu | B/Khu (R) | 132/220 KV G/S B/Khu | Golf city | 89216 |  |  |  | 07:00 | 11:00 |  | Golf city
8 | IESCO | IBD | B/Khu | Patriata | 132KV Kuldana Murree | Upper Topa | 13705 | 11.03.2025 18.03.2025 25.03.2025 |  |  | 07:00 | 11:00 | Shifting of HT line Mohra Batnara | Mohra Batnara, Sambal Bia, Ghora Bastal, Khajut, Hokra Karri.
9 | IESCO | IBD | B/Khu | B/Khu | 132/220 KV G/S B/Khu | Pir Sohawa | 122503 | 16.03.2025 27.03.2025 |  |  | 07:00 | 11:00 | Shifting HT line Madrasa Vill Talhar ibd | Kotla, Pir Sohawa , Kohala bala and Surrounding area
10 | IESCO | IBD | Bhara Kahu | B/K Rural | University Grid 220KVA | Bari Imam | 89212 | 07-03-2025 10-03-2025 16-03-2025 24-03-2025 27-03-2025 |  |  | 07:00 | 11:00 | Bifurcation of Bari Imam Feeder | Bari Imam Mall Pur
11 | IESCO | IBD | No.I | F-6 | University Grid 220KVA | Punjab House | 122506 |  |  |  | 07:00 | 11:00 |  | Independent
12 | IESCO | IBD | No.I | F-6 | University Grid 220KVA | Khayban e Iqbal | 122505 |  |  |  | 07:00 | 11:00 |  | Independent
13 | IESCO | IBD | Bhara Kahu | B/K Rural | University Grid 220KVA | Pir Sohawa | 122503 |  |  |  | 07:00 | 11:00 |  | Pir Sohawa and Sarrounding
14 | IESCO | IBD | Bhara Kahu | B/K Rural | University Grid 220KVA | Quied E Azam University | 122502 |  |  |  | 07:00 | 11:00 |  | Quied E Azam University
15 | IESCO | Cantt | Mandra | Wadala | 132KV Old Rawat | New Kalyam | 17721 | 08.03.2025 11.03.2025 15.03.2025 24.03.2025 | - |  | 07:00 | 11:00 | Area Planing of 11KVA Jatha Hathial and 11KVA Pind Jatla Feeder | Shah Khai awan & Sorrounding Area
16 | IESCO | Cantt | Mandra | Wadala | 132KV Old Rawat | Basali | 017728 |  | - |  | 07:00 | 11:00 |  | Basali & sorrounding area
17 | IESCO | Cantt | Mandra | Wadala | 132KV Old Rawat | Pind Jhatla | 017727 |  | - |  | 07:00 | 11:00 |  | Suparco & sorrounding area | Subject to avaialbility of NOC.
18 | IESCO | Cantt | Mandra | Wadala | 500KV New Rawat | Islamabad Feed Mill | 064511 |  | - |  | 07:00 | 11:00 |  | IFM & sorrounding area
19 | IESCO | Cantt | Mandra | Wadala | 500KV New Rawat | Jatha Hathial | 064503 |  | - |  | 07:00 | 11:00 |  | Jatha Hathial & sorrounding area
20 | IESCO | Cantt | Mandra | Wadala | 500KV New Rawat | Lab-I | 64504 |  | - |  | 07:00 | 11:00 |  | Lab-I & Sorrounding Area
21 | IESCO | Cantt | Mandra | Wadala | 500KV New Rawat | Lab -II | 64505 |  | - |  | 07:00 | 11:00 |  | Lab-II & Sorrounding Area
22 | IESCO | Cantt | Mandra | Wadala | 500KV New Rawat | Industrial | 064502 |  | - |  | 07:00 | 11:00 |  | Industrial & sorrounding area
23 | IESCO | Cantt | Mandra | Wadala | 500KV New Rawat | Reliance Waving Mill | 064501 |  | - |  | 07:00 | 11:00 |  | Reliance Weaving Mill & sorrounding area
24 | IESCO | Cantt | Mandra | Wadala | 500KV New Rawat | Bhall | 064507 |  | - |  | 07:00 | 11:00 |  | Bhall & sorrounding area
25 | IESCO | Cantt | Tariqabad | Adyala | 500KV New Rawat | Jarrar Camp | 064510 |  | - |  | 07:00 | 11:00 |  | Jarrar Camp & sorrounding area
1 | IESCO | Jhelum | Jhelum-II | Rural | Jhelum | Pakhwal | 7720 | 10.03.25 12.03.25 15.03.25 17.03.25 19.03.25 24.03.25 26.03.25 |  |  | 0700 | 1100 | Stringing of 11KV pakhwal feeder | Pakhwal etc
2 | IESCO | Jhelum | Jhelum-II | Rural | Jhelum | F-9 (Chak Daulat) | 7709 |  |  |  | 0700 | 1100 |  | Chak Doulat e
3 | IESCO | Jhelum | Jhelum-II | Rural | Jhelum | Jakkar | 7714 |  |  |  | 0700 | 1100 |  | Jakkar Etc
4 | IESCO | Jhelum | Jhelum-2 | Dina City | Dina | Mumtaz Shaheed | 46809 | 11.03.25 13.03.25 |  |  | 0700 | 1100 | Stinging of 11KV Rohtas feeder | Mumtaz Shaheed
5 | IESCO | Jhelum | Jhelum-2 | Dina City | Dina | Khokhran | 46811 | 13.03.25 |  |  | 0700 | 1100 |  | Khokhran
6 | IESCO | Jhelum | Jhelum-2 | Dina -I | Dina | M. Riaz Shaheed | 46808 |  |  |  | 0700 | 1100 |  | M. Riaz Shaheed
7 | IESCO | Jhelum | Jhelum-2 | Dina City | Dina | Dina-4 ( City) | 46804 |  |  |  | 0700 | 1100 |  | Dina-4 ( City)
8 | IESCO | Jhelum | Jhelum-2 | Dina City | Dina | Co.Muhammad Akram | 46806 | 11.03.25 13.03.25 |  |  | 0700 | 1100 |  | Co.Muhammad Akram
1 | IESCO | Jhelum | G.Khan | City GK | G.Khan | Matwa | 4906 | 26.03.25 |  |  | 0700 | 1000 | Execution of LV Works & PSH works | Matwa etc
2 | IESCO | Jhelum | G.Khan | City GK | G.Khan | Karoli | 4920 | 15.03.25 19.03.25 |  |  | 0700 | 1000 |  | W.No.19 etc
3 | IESCO | Jhelum | G.Khan | City GK | G.Khan | Ward No.08 | 4911 | 13.03.25 18.03.25 |  |  | 0700 | 1000 |  | Main Bazar etc
4 | IESCO | Jhelum | G.Khan | Sohawa | G.Khan | Kulia | 4909 | 28.03.25 |  |  | 0700 | 1000 |  | Waheeklan etc
5 | IESCO | Jhelum | G.Khan | Guliana | G.Khan | Thakra | 4921 | 24.03.25 |  |  | 0700 | 1000 |  | Cheena etc
6 | IESCO | Jhelum | G.Khan | Guliana | G.Khan | Guliana | 4902 | 17.03.25 |  |  | 0700 | 1000 |  | Guliana etc
7 | IESCO | Jhelum | G.Khan | Bhadana | G.Khan | Islam Pura | 4910 | 11.03.25 21.03.25 |  |  | 0700 | 1000 |  | Jand Najar etc
8 | IESCO | Jhelum | G.Khan | Bhadana | G.Khan | Qazian | 4912 | 27.03.25 |  |  | 0700 | 1000 |  | Qazian etc
1 | IESCO | CHAKWAL | Dhudial | Khan Pur | 132 KV Padshahan | Khanpur | 079107 | 12.03.2025 17.03.2025 19.03.2025 |  |  | 07:00 | 11:00 | For completion of Area Planning of 11 KV Mulhal Mughlan Feeder and 11 KV Dhrugi Rjgan Feeder emanating from 132 KV Padshan G.S (2K25-456-ELR-HT-10) | Surrounding area of Feeder | -
2 | [5 empty] | Dhurugi Rajgan | 79113 | 11.03.2025 18.03.2025 |  |  | 07:00 | 11:00 |  |  | -
3 | [5 empty] | Mulhal Mughlan | 79101 |  |  |  | 07:00 | 11:00 |  |  | -
1 | IESCO | City | Satellite Town | Gangal | I-8 | AFOHS | 61131 | 11/03/2025 12/03/2025 14/03/2025 |  |  | 09:00 hrs. | 12:00 hrs. | Stringing work IRO Extension of load from 10 kW to700 kW (580KW Ext.) IRO KRL Medical Centre Chatri Chowk Rwp | Air force Officer Housing Soc.
2 |  |  |  |  | Tramri | Khanna-II | 105514 | 11/03/2025 14/03/2025 | [5 empty] | Dk Gangal,KRL road,AL-noor Cly & surroundings.
1 | IESCO | City | Westridge | Tarnol | G-13 | NUST Road | 106708 | 12.03.2025 27.03.2025 |  |  | 08:00 hrs. | 11:00 hrs. | Installation of T/F & stringing IRO LV work Nr.Fayyaz plaza | NUST road & surroundings.
2 | IESCO | City | Westridge | Seham | KTM | Chakra | 8604 | 20.03.2025 25.03.2025 |  |  |  |  | Installation of T/F & stringing conversion IRO LV work Saeed toota house | Chistiabad,Muhammadi Cly,Dk.Sada
3 | IESCO | City | Westridge | Tarnol | KTM | Azharabad | 8620 | 20.03.2025 26.03.2025 |  |  |  |  | Installation of T/F of LV work Sajid Lane Dk.Salman | Peshawar Road, Pind Paracha &surroundings
4 | IESCO | City | Westridge | Westridge | Pirwadhai | Askari XI | 43325 | 17.03.2025 27.03.2025 |  |  |  |  | Installation of T/F of LV work Saqi General Store | Askari-XI lane 1 to 7 st.No.1 to14
5 | IESCO | City | Westridge | Kamalabad | Kamalabad | Captain Amir | 1018 | 25.03.2025 |  |  |  |  | Installation of T/F of LV work Nr.Mursaleen House | Kamalabad,Aslam market,Moh Shah faisal
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rajjar | A.E (T) SS&TL Sub Division Mangla | 132KV Dudyal (DDL-3) - Chakswari (CKS-3) along with related earth switch |  |  | 13-03-2025, & 15-03-2025 |  |  | 06:00 | 15:00 | For stringing between Loc No. 25 to 30 | No area will be affected as 132KV Islamgarh & Chakswari will be fed from Mirpur.
2 |  |  |  |  | 132KV Dudyal (DDL-4) - Gulpur (E4Q1) |  |  | 16-03-2025 |  |  | 06:00 | 15:00 | For Bundling arrangement at Loc No. 66 as per interim arrangement | No area will be affected as 132KV Kotli & Khui Ratta will be fed from Tararkhal side or Gulpur side. Islamgarh & Chakswari will be fed from Mirpur & Dudyal. However, 50MW load management will be required.
3 |  |  |  |  | 132KV Chakswari (CKS-1) - Khui Ratta (No Load)
4 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rajjar | A.E (T) SS&TL Sub Division Mangla | 132KV Dudyal (DDL-4) - Gulpur (E4Q1) |  |  | 16-03-2025 To 16-06-2025 (Contineous) |  |  | 16-03-2025 07:00 Hrs | 16-06-2025 18:00 Hrs | For stringing of 2nd circuit Dudyal - Gulpur T/L | No Area will be affected as Gulpur will be evacuted from Kotli as well as by Chakswari - Dudyal (DDL-3) during interim arrangement through bundle at Loc No. 66 at Jirahi camp side.
1 | IESCO | IBD | NO.II | I-10 | I-10 | I-10/1 | 6432 | 12-03-2025 19-03-2025 26-03-2025 |  |  | 07:00 | 11:00 | Bifurcation of 11 KV I-10/1 feeder from I-10 G/S to Newly constructed 132 KV I-11 G/S | I-10/1
2 | IESCO | IBD | NO.II | I-10 | H-11 | I-10/2 | 72704 | [6 empty] | I-10/2
3 | IESCO | IBD | NO.II | I-10 | I-11 | New I-10/1 | Not allocated | [6 empty] | New I-10/1
4 | IESCO | IBD | NO.II | I-10 | I-11 | New I-10/2 | [7 empty] | New I-10/2
77 | IESCO | Cantt | Tariqabad | Adyala | 132KV Adyala | Defence Road | 109113 | 12.03.2025 | - |  | 08:00 | 11:00 | For dismantling/ shifting of poles at Khawaja Corporation Chowk Adyala Road Rawalpindi | Defence Road & sorrounding area | For Safety Purpose
78 | IESCO | Cantt | Tariqabad | Tariqabad | 132KV Adyala | Hamayoun 1 | 109111 |  | - |  | 08:00 | 11:00 |  | Humayoun Road & sorrounding area
79 | IESCO | Cantt | Tariqabad | Adyala | 132KV Adyala | Rose Lane | 109112 |  | - |  | 08:00 | 11:00 |  | Rose Lane & sorrounding area
80 | IESCO | Cantt | Tariqabad |  | 132KV Adyala | Adyala | 109106 |  | - |  | 08:00 | 11:00 |  | Adyala & sorrounding area
81 | IESCO | Cantt | Tariqabad |  | 132KV Adyala | Kalyal | 109101 |  | - |  | 08:00 | 11:00 |  | Kalyal & sorrounding area
82 | IESCO | Cantt | Tariqabad | Tariqabad | 132KV Chaklala | Humayoun Road | 002525 |  | - |  | 08:00 | 11:00 |  | Humayoun Road & sorrounding area