## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date | Existing Operation Maintenance Date | Proposed Change Date for Operation Maintenance | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
5 | IESCO | Cantt | Cantt | Sowan | 132KV Chaklala | Chaklala | 2503 | 26.01.2025 17.02.2025 19.02.2025 24.02.2025 26.02.2025 | 15.01.2025 |  | 09:00 | 14:00 | for Tentative D/N for External Electrification of Takebeer 1 Project (A project of CWO) Kot Jabbi Rwp | Chaklala & Surrounding
6 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Rehmatabad-I | 2519 |  | 21.01.2025 27.01.2025 |  | 09:00 | 14:00 |  | Rehmatabad & Surrounding
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) Sub Divisoin No-II Islamabad | 132KV Kahuta City (KHC-2) - Palandri (PLD-3) along with related earth Switch. |  |  | 02-02-2025, 04-02-2025, 06-02-2025, 08-02-2025, 10-02-2025, 12-02-2025, 15-02-2025, 17-02-2025, 19-02-2025, 22-02-2025, 24-02-2025, 26-02-2025 Daily Basis) |  |  | 08:00 Hrs | 16:00 Hrs | For Erection of ZM-1 Towers | No area will be affected as 132KV GSS Kahuta City along with Chaint will be fed from 132KV GSS KRL Kahuta side & Palandri, Tararkhal & Hajeera will be fed from Kotli side.
2 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rajjar | A.E (T) SS&TL Sub Division Mangla | 132KV Dudyal (DDL-4) - Gulpur (E4Q1) & 132KV Dudyal (DDL-3) - Chakswari (CKS-3) |  |  | 01-02-2025, 03-02-2025, 09-02-2025, 11-02-2025, 18-02-2025, 20-02-2025, 23-02-2025, 25-02-2025, 27-02-2025 Daily Basis) |  |  | 07:00 Hrs | 18:00 Hrs | For Erection/Stringing between Loc No. 25 to 34. | No Area will be affected as 132 kv Kotli and Khoi Ratta GSS will be fed from Tararkhal Side or Gulpur side. 132 Kv Islamgarh & Chakswari will be fed from Mirpur side. However, 50 MW load management will be carried out in case of contigency/over loading.
1 | IESCO | RWP | Cantt | Civil Line | Chaklala | RIC | 2534 | 06-02-2025 10-02-2025 13-02-2025 17-02-2025 20-02-2025 24-02-2025 27-02-2025 | 02.02.2025 |  | 09:00 | 14:00 | Tentative D/N for External Electrification of Takbeer 1 Project ( A Project of CWO) Kot Jabbi Rwp | Civil Line
2 | IESCO | RWP | Satellite Town | Chandni Chowk | Chaklala | Benazir Bhutto | 2537 |  | Nil |  | 09:00 | 14:00 |  | Chandni Chowk
3 | IESCO | RWP | Cantt | Chaklala | Chaklala | Gracy Line | 2533 |  | Nil |  | 09:00 | 14:00 |  | Gracy Line
4 | IESCO | RWP | Satellite Town | Gulzar e Qaid | Chaklala | Sector-IV | 2536 | 03-02-2025 08-02-2025 15-02-2025 22-02-2025 25-02-2025 | 04.02.2025 11.02.2025 18.02.2025 25.02.2025 |  | 09:00 | 14:00 |  | Sector-IV
5 | IESCO | RWP | Satellite Town | Gulzar e Qaid | Chaklala | Airport Society | 2526 |  | 01.02.2025 06.02.2025 12.02.2025 19.02.2025 26.02.2005 |  | 09:00 | 14:00 |  | Airport Society
6 | IESCO | RWP | City | Zafar-ul Haq | Chaklala | DK Hukam Dad | 2527 |  | 12.02.2025 17.02.2025 20.02.2025 24.02.2025 |  | 09:00 | 14:00 |  | DK Hukam Dad
7 | IESCO | RWP | City | Zafar-ul Haq | Chaklala | Tamasamabad | 2518 |  | 03.02.2025 08.02.2025 15.02.2025 19.02.2025 26.02.2025 |  | 09:00 | 14:00 |  | Tamasamabad
8 | IESCO | RWP | Cantt | Chaklala | Chaklala | VVIP | 2514 |  | Nil |  | 09:00 | 14:00 |  | VVIP
9 | IESCO | RWP | Cantt | Jhanda | Chaklala | MES | 2506 |  | Nil |  | 09:00 | 14:00 |  | MES
10 | IESCO | RWP | Cantt | Chaklala | Chaklala | PAF | 2509 | 03-02-2025 08-02-2025 15-02-2025 22-02-2025 25-02-2025 | 03.02.2025 08.02.2025 17.02.2025 22.02.2025 27.02.2025 |  | 09:00 | 14:00 | Tentative D/N for External Electrification of Takbeer 1 Project ( A Project of CWO) Kot Jabbi Rwp | PF
11 | IESCO | RWP | Cantt | Chaklala | Chaklala | Rehmatabad-I | 2519 |  | 01.02.2025 10.02.2025 19.02.2025 25.02.2005 |  | 09:00 | 14:00 |  | Rehmatabad-I
12 | IESCO | RWP | Cantt | Chaklala | Chaklala | Chaklala | 2503 |  | Nil |  | 09:00 | 14:00 |  | Chaklala
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | AE(T) Margalla | 132Kv Fateh Jang (FTJ-1) - Bahtermore (BMW-1) T-off Fauji Cement Plant (ISO-101) along with related earth switch |  |  | 05-02-2025 |  |  | 09:00 Hrs | 12:00 Hrs | For opening the jumpers of Loc No. 95 for erection of towers & stringing of conductor between loc No. 68 to 95 for remodeling of 132KV T/Line New Wah to Fateh Jang to Bahtermore | 132KV Fauji Cement Plant will be affected. However, 132KV GSS Bahtermore will be fed from New Wah side & 132KV GSS Fateh Jang will be fed from Sangjani side.
[5 empty] | 132KV Bahtermore (BMW-1) to Loc No. 95. |  |  | 05-02-2025 to 06-03-2025 (Contineous) |  |  | 05-02-2025 09:00 Hrs | 06-03-2025 16:00 Hrs |  | During the Shut Down 132KV T/Line Bahtermore to Loc No. 95 will remain off & remaining portion from Loc No. 95 to Fateh Jang will be energized.
5 | IESCO | IBD | Bhara Kahu | B/K Rural | University Grid 220KVA | Bari Imam | 89212 | 04-02-2025 08-02-2025 24-02-2025 27-02-2025 | 08.02.2025 12.02.2025 |  | 09:00 | 14:00 | Bifurcation of Bari Imam Feeder | Bari Imam Mall Pur
6 | IESCO | IBD | No.I | F-6 | University Grid 220KVA | Punjab House | 122506 |  | Nil |  | 09:00 | 14:00 |  | Independent
7 | IESCO | IBD | No.I | F-6 | University Grid 220KVA | Khayban e Iqbal | 122505 |  | Nil |  | 09:00 | 14:00 |  | Independent
8 | IESCO | IBD | Bhara Kahu | B/K Rural | University Grid 220KVA | Pir Sohawa | 122503 |  | 01.02.2005 20.02.2025 24.02.2025 |  | 09:00 | 14:00 |  | Pir Sohawa and Sarrounding
9 | IESCO | IBD | Bhara Kahu | B/K Rural | University Grid 220KVA | Quied E Azam University | 122502 | 24-02-2025 27-02-2025 | 15.02.2025 |  | 09:00 | 14:00
10 | IESCO | Cantt | Mandra | Wadala | 132KV Old Rawat | Basali | 17728 | 06.02.2025 10.02.2025 15.02.2025 19.02.2025 24.02.2025 27.02.2025 | 03.02.2025 06.02.2025 10.02.2025 15.02.2025 19.02.2025 24.02.2025 27.02.2025 |  | 09:00 | 14:00 | Shifting of HT / LT line IRO Rawalpindi Ring Road Project | Basali & surrounding area
11 | IESCO | Cantt | Mandra | Wadala | 500KV New Rawat | Jhata Hatyal | 64503 |  | 03.02.2025 06.02.2025 10.02.2025 15.02.2025 19.02.2025 24.02.2025 27.02.2025 |  | 09:00 | 14:00 |  | Jhata hatyal & Surrounding areas
12 | IESCO | Cantt | Mandra | Wadala | 132KV Old Rawat | New kalyam | 17721 | 06.02.2025 10.02.2025 15.02.2025 19.02.2025 24.02.2025 27.02.2025 | 03.02.2025 06.02.2025 10.02.2025 15.02.2025 19.02.2025 24.02.2025 27.02.2025 |  | 09:00 | 14:00 | Shifting of HT / LT line IRO Rawalpindi Ring Road Project | New Kalyam & Surrounding areas
13 | IESCO | Cantt | Mandra | Wadala | 500KV New Rawat | Industrial | 64502 |  | 03.02.2025 06.02.2025 10.02.2025 15.02.2025 19.02.2025 24.02.2025 27.02.2025 |  | 09:00 | 14:00 |  | Industrial & Surrounding areas
14 | IESCO | Cantt | Mandra | Mandra | 500KV New Rawat | Gumti | 64512 |  | No scheduled |  | 09:00 | 14:00 |  | Gumti & Surrounding areas
15 | IESCO | Cantt | Mandra | Wadala | 132KV Old Rawat | Old Kalyam | 17710 |  | 03.02.2025 06.02.2025 15.02.2025 19.02.2025 24.02.2025 27.02.2025 |  | 09:00 | 14:00 |  | Kalyam & surrounding areas
16 | IESCO | Cantt | Mandra | Chak Bali | 500KV New Rawat | Bhal | 64507 |  | 03.02.2025 06.02.2025 10.02.2025 15.02.2025 19.02.2025 24.02.2025 27.02.2025 |  | 09:00 | 14:00 |  | Bahl & surounding areas
17 | IESCO | Cantt | T/Abad | Dhaimial | 132KV Ranyal | Moorat | 120405 |  | 03.02.2025 10.02.2025 19.02.2025 27.02.2025 |  | 09:00 | 14:00 |  | Moorat & Surrounding areas
18 | IESCO | Cantt |  | Adiala | 132KV Adiala | Khasala | 109108 |  | 03.02.2025 10.02.2025 19.02.2025 27.02.2025 |  | 09:00 | 14:00 |  | Khasala & Surrounding areas
19 | IESCO | Cantt |  | Adiala | 500KV Rawat | Jarar Camp | 64510 |  | Nil |  | 09:00 | 14:00 |  | Jarrar Camp
12 | IESCO | Cantt | Rawat | RAWAT | 132KV Sowan | Zaraj-I | 87411 | 10.02.2025 18.02.2025 28.02.2025 | 10.02.2025 |  | 09:00 | 14:00 | For reconductoring of Fauji Foundation Feeder & shifting of HT/ LT Lines Deposit Work Potohar Avenue | Zaraj-I & Surrounding area
13 | IESCO | Cantt | Rawat | RAWAT | 132KV Sowan | Zaraj-II | 87423 |  | 10.02.2025 |  | 09:00 | 14:00 |  | Zaraj-II & Surrounding area
14 | IESCO | Cantt | Rawat | RAWAT | 132KV Sowan | Zeta-I | 87424 |  | - |  | 09:00 | 14:00 |  | Zeta Mall & Surrounding area
15 | IESCO | Cantt | Rawat | RAWAT | 132KV Sowan | IST | 87421 |  | - |  | 09:00 | 14:00 |  | IST Universty & Surrounding area
16 | IESCO | Cantt | Rawat | Rawat | 132KV Old Rawat | New Rawat | 17701 |  | 11.02.2025 18.02.2025 |  | 09:00 | 14:00 |  | AOWHS & Surrounding area
17 | IESCO | Cantt | Cantt | Sowan | 132KV Sowan | Mora Nagial | 87422 |  | 04.02.2025 08.02.2025 12.02.2025 18.02.2025 22.02.2025 26.02.2025 |  | 09:00 | 14:00 |  | Mora Nagial & Surrounding area
7 | IESCO | Cantt | Mandra | Wadala | 132KV Old Rawat | Pind Jhatla | 017727 | 10.02.2025 15.02.2025 19.02.2025 24.02.2025 27.02.2025 | 03.02.2025 08.02.2025 12.02.2025 18.02.2025 22.02.2025 27.02.2025 |  | 09:00 | 14:00 | For area planning of 11KV Jatha Hathial & 11KV Pind Jhatla Feeder | Suparco & sorrounding area
8 | IESCO | Cantt | Mandra | Wadala | 500KVA New Rawat | Islamabad Feeder Mill | 64511 |  | - |  | 09:00 | 14:00 |  | Islamabad Feed Mill & Sorrounding Area
9 | IESCO | Cantt | Mandra | Wadala | 500KV New Rawat | Lab-I | 64504 |  | - |  | 09:00 | 14:00 |  | Lab-I & Sorrounding Area
10 | IESCO | Cantt | Mandra | Wadala |  | Lab -II | 64505 |  | - |  | 09:00 | 14:00 |  | Lab-II & Sorrounding Area
11 | IESCO | Cantt | Mandra | Wadala |  | Relance Weaving Mill | 64501 |  | - |  | 09:00 | 14:00 |  | Relince & Sorrounding Area
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | AE(T) Margalla | 132Kv Wah-83 controlling 132/66KV 31.5/140MVA Power Transformer T-3 at 132KV GSS New Wah |  |  | 06-02-2025 to 15.03.2025 (Contineous) |  |  | 06.02.2025 0900Hrs | 15.03.2025 0900Hrs | For dismentling the existing 132KV Transformer Bay & 66KV Line Bay Haripure-Havelian to Spare this line bay for 132KV T/Line New wah to Bahtarmore | No Area will be affected, 66Kv GSS Haripure will be fed from Havelian (PESCO)
14 | IESCO | IBD | B/Khu | J/Gali | 132KV Kuldana Murree | PC | 13708 | 15-02-2025 26-02-2025 | 03-02-2025 20-02-2025 26-02-2025 |  | 09:00 | 14:00 | Estimate for shifting of HT Line due to Road Extension work of khuldana at khuldana Murree | PC Hotel
15 | IESCO | IBD | B/Khu | Patriata | 132KV Kuldana Murree | TDCP | 13717 |  | 10-02-2025 17-02-2025 25-02-2025 |  | 09:00 | 14:00 |  | Patriata Chair left | AM Shut down on 11KV feeder dated 25.02.2025 is hereby cancelled
16 | IESCO | IBD | B/Khu | J/Gali | 132KV Kuldana Murree | MCM | 13716 |  | 06-02-2025 13-02-2025 |  | 09:00 | 14:00 |  | Murree Military college
17 | IESCO | IBD | B/Khu | J/Gali | 132KV Kuldana Murree | GHARIAL | 13711 |  | 06-02-2025 13-02-2025 |  | 09:00 | 14:00 |  | J/gali Bazar Gjarial camp.Kashmiri Bazar,seher bagla Aliot
18 | IESCO | IBD | B/Khu | J/Gali | 132KV Kuldana Murree | KOHALLA | 13701 |  | 03-02-2025 20-02-2025 26-02-2025 |  | 09:00 | 14:00 |  | Kani Tak, Mohra Sharif ,Rawat Osai Dewel Malkot
19 | IESCO | IBD | B/Khu | Murree | 132KV Kuldana Murree | Sunny Bank | 13704 |  | 12-02-2025 19-02-2025 |  | 09:00 | 14:00 |  | 12 Div, Moter Agency , Sunny Bazar , chatta morh.
20 | IESCO | IBD | B/Kahu | J/Gali | Murree | Barrian | 13706 |  | 10-02-2025 17-02-2025 24-02-2025 |  | 09:00 | 14:00 |  | Ratti Gali, Sawar Gali, Kalli Matti, Barrian
21 | IESCO | City | Westridge | Tarnol | Tarnol | Bajnial-I | 106903 | 13.02.2025 19.02.2025 26.02.2025 | 2025-02-13 |  | 09:00 | 14:00 | Nr.Boys School Bajnial Barkat House Village Bajnial | Bajnial & surroundings
22 | IESCO | City | Westridge | Tarnol | Tarnol | Bajnial-II |  |  |  |  | 09:00 | 14:00
23 | IESCO | City | Westridge | Misrial | Pirwadhai | Madina Colony | 43334 | 22.02.2025 26.02.2025 | 10/02/2025 15/02/2025 20/02/2025 26/02/2025 |  | 09:00 | 14:00 | Madina Cly Gali No.04 &07 | Madina Colony & surroundings
37 | IESCO | City | Westridge | Tarnol | KTM | Shams Cly | 8628 | 11.02.2025 15.02.2025 18.02.2025 20.02.2025 22.02.2025 25.02.2025 27.02.2025 | 22.02.25 |  | 09:00 | 14:00 | Re-Conductoring of Shammas Colony Feeder | Shams Cly & surroundings.
38 | IESCO | City | Westridge | Tarnol | KTM | Modern Flour Mill | 8603 |  | Nil |  | 09:00 | 14:00 |  | Modern floor Mill & surroundings.
1 | IESCO | IBD | Div-1 | Nilore | 132/220kv G/S B/Khu | Athal | 89217 | 27-02-2025 | 03-02-2025 20-02-2025 26-02-2025 |  | 09:00 | 14:00 | Bifurcation of Shah Pur Feeder/ Installation of HT Str 58' and Strninging of HT line in R/O External Electrification of Park View City Housing Society | Bhara Kahu Bazar, Sanjalian and Surrounding Area
2 | IESCO | IBD | B/Khu | B/Khu (U) | 132/220 KV G/S B/Khu | B/ Khu-I | 89201 |  | 08-02-2025 19-02-2025 |  | 09:00 | 14:00 |  | Madina Town, Nain Sukh,and Surrounding Area
3 | IESCO | IBD | B/Khu | B/Khu (U) | 132/220 KV G/S B/Khu | B/ Khu-II | 89219 |  | 08-02-2025 19-02-2025 |  | 09:00 | 14:00 |  | Athal Road, Tumair, Athal vill.
18 | IESCO | City | S/Town | Gulzar-e-Quiad | Chaklala | Gulzar-e-Quiad | 2532 | 20.02.2025 27.02.2025 | 15/02/2025 22/02/2025 |  | 09:00 | 14:00 | Stringing of HT line IRO Bifurcation of 11-KV Gulzar Qiuiad emanating form 132-KV Grid Station Chaklala under ELR head (2k24-431-ELR-HT-14) | Dk Gangal,Dk.Sher Zaman,KRL road,Al-noor Cly
19 | IESCO | City | S/Town | Gangal | Chaklala | Khanna Road | 2517 |  | 2025-02-22 |  | 09:00 | 14:00 |  | New Gulzar-E-Quiad, Magistrate Cly & surroundings
20 | IESCO | City | S/Town | Gulzar-e-Quiad | Chaklala | Gangal | 2512 |  | 17/02/2025 24/02/2025 |  | 09:00 | 14:00 |  | Gulzar-E-Quiad,Shah Khalid Cly,Dk Anwar Magistrate Cly
21 | IESCO | City | City | Zafar-Ul-Haq | Chaklala | Tehmasimabad | 2518 | 27-02-2025 | 15/02/2025 19/02/2025 26/02/2025 |  | 09:00 | 14:00 |  | Temasimabad & surroundings
22 | IESCO | City | City | Zafar-Ul-Haq | Chaklala | Dk.Hukamadad | 2527 |  | 17/02/2025 20/02/2025 24/02/2025 |  | 09:00 | 14:00 |  | Dk.Hukamdad & surroundings
1 | IESCO | City | Westridge | Seham | KTM | Range Road | 8627 | 15.02.2025 19.02.2025 27.02.2025 | 19/02/2025 27/02/2025 |  | 9:00: am | 12:00 pm | Re-conductoriing of 11-KV Shams Colony Feeders | Mukarram Town, Mohallah Rajputan, Range Road
2 | IESCO | City |  |  |  | Seham | 8618 | [6 empty] | Usmania Colony, Qadria Colony, Farooq Abad
1 | IESCO | City | Westridge | Tarnol | Tarnol | Shalimar City | 106903 | 18.02.2025 20.02.2025 24.02.2025 27.02.2025 | 13-02-2025 |  | 09:00 | 14:00 | Stringing & Erection of HT STR 58 for Faisal Town. | Shalimar Town
2 | IESCO | City | Westridge | Tarnol | Tarnol | Top City | 104905 |  | Nil |  | 09:00 | 14:00 |  | Top City
3 | IESCO | City | Westridge | Tarnol | Tarnol | Mumtaz City | 104906 |  | Nil |  | 09:00 | 14:00 |  | Mumtaz City
4 | IESCO | City | Westridge | Tarnol | Tarnol | F-17/I | 106901 |  | Nil |  | 09:00 | 14:00 |  | F-17 & Surroundings
5 | IESCO | City | Westridge | Tarnol | Tarnol | F-17/II | 106902 |  | Nil |  | 09:00 | 14:00 |  | F-17 & Surroundings
6 | IESCO | City | Westridge | Tarnol | Tarnol | Nogazi | 104901 |  | 12/02/2025 24/02/2025 |  | 09:00 | 14:00 |  | Nogazi Main F/Jang Road & Surrounding area
7 | IESCO | City | Westridge | Tarnol | Tarnol | Fazaiya-I | 104902 |  | Nil |  | 09:00 | 14:00 |  | Fazaiya & surroundings
8 | IESCO | City | Westridge | Tarnol | Tarnol | Fazaiya-II | 104904 |  | Nil |  | 09:00 | 14:00 |  | Fazaiya & surroundings
9 | IESCO | City | Westridge | Tarnol | Tarnol | Bajnial-I | 106903 |  | 2025-02-13 |  | 09:00 | 14:00 |  | Vlg Bajnial & surroundings
10 | IESCO | City | Westridge | Tarnol | Tarnol | Bajnial-II | 104911 |  | 2025-02-13 |  | 09:00 | 14:00 |  | Vlg Bajnial & surroundings
11 | IESCO | City | Westridge | Tarnol | Tarnol | Wapda Cly | Newly energized |  | Nil |  | 09:00 | 14:00 |  | Wapda Cly
12 | IESCO | City | Westridge | Tarnol | Tarnol | Gandhara City | 104913 |  | Nil |  | 09:00 | 14:00 |  | Gandhara City
13 | IESCO | Cantt | Tariqabad | Q.A Colony | 132KV Ranyal | Qureshi-Abad | 120401 | 26.02.2025 | 12.02.2025 19.02.2025 22.02.2025 |  | 09:00 | 14:00 | For HT stringing work iro External Electrification iro Rehbar Colony Housing Scheme Mouza Hayal Ranyal & Hayal Dhamial Chakri Road Rawalpindi | Qureshi-Abad & sorrounding area
14 | IESCO | Cantt | Tariqabad | Q.A Colony | 132KV Ranyal | Girja-1 | 120402 |  | 10.02.2025 17.02.2025 26.02.2025 |  | 09:00 | 14:00 |  | Girja-I & sorrounding area
15 | IESCO | Cantt | Tariqabad | Dhamial | 132KV Ranyal | Ranyal | 120403 |  | 13.02.2025 20.02.2025 |  | 09:00 | 14:00 |  | Ranyal & sorrounding area
16 | IESCO | Cantt | Rawat | Kallar Syedan | 132KV Kallar | Kallar City | 098104 | 18.02.2025 22.02.2025 27.02.2025 | 27.02.2025 |  | 09:00 | 14:00 | For 11KV Kallar Syedan-II feeder | Kallar Syedan & sorrounding area
17 | IESCO | Cantt | Rawat | Kallar Syedan | 132KV Kallar | Doberan | 098106 |  | 11.02.2025 15.02.2025 22.02.2025 |  | 09:00 | 14:00 |  | Doberan & sorrounding area
18 | IESCO | Mirpur | Dhudial City | Dhudial City-I | 132KV Dhudial | City-II | 91102 | 18.02.2025 20.02.2025 23.02.2025 25.02.2025 27.02.2025 |  |  | 08:30 | 17:00 | For strininging between location # 25 to 34 | City-II
19 | IESCO | Mirpur | Dhudial City | Dhudial City-I | 132KV Dhudial | Onnah Town-I | 91108 | 25.02.2025 27.02.2025 |  |  | 08:30 | 17:00 | For strininging between location | Onnah Town-I
3 | IESCO | Cantt | Cantt | Chaklala | 132KV Cantt | PAF | 002509 | 27.02.2025 | 08.02.2025 17.02.2025 22.02.2025 27.02.2025 |  | 09:00 | 14:00 |  | PAF & sorrounding area
4 | IESCO | Cantt | Cantt | Jhanda | 132KV Chaklala | VVIP | 002514 |  | Nil |  | 09:00 | 14:00 |  | MES & sorrounding area
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | A.E (T) Sub Division Margalla | 10/13MVA Power Transformer T-1 at 132KV Lakkarmar |  |  | 19-02-2025 To 28-02-2025 (Contineous) |  |  | 19-02-2025 08:00 Hrs | 28-02-2025 16:00 Hrs | For De-Hydration of Power Tranformer | No area will be affected asload of Power Transformer T-1 will be shifted to Power Transformer T-2 through Bus Coupler.
4 | IESCO | Jhelum | Jhelum-2 | Dina City | Dina | Dina-4 (City) | 46804 | 26.02.2025 | [5 empty] | Dina City
5 | IESCO | Jhelum | Jhelum-2 | Dina City | Dina | Co.Muhammad Akram | 46806 | [6 empty] | Dina City
6 | IESCO | Jhelum | Jhelum-2 | Dina-II | Dina | Dina-I (Bakrala) | 46801 | [6 empty] | Barkala etc
7 | IESCO | Jhelum | Jhelum-2 | Dina City | Dina | Mumtaz Shaheed | 46809 | [6 empty] | Nia Moh:, etc
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | A.E (T) Sub Division Margalla | 132KV Fateh Jang (FTJ-4) - Basal (BSL-2) T/Line along with related earth switch |  |  | 25-02-2025 To 06-03-2025 (Contineous) |  |  | 25-02-2025 08:00 Hrs | 06-03-2025 18:00 Hrs | For Safety purpose during erection of 132KV Towers | No area will be affected as 132KV GSS Basal will be fed from 132KV GSS Jand side.
1 | IESCO | Islamaabd | Bahra Kahu | Bahra Kahu (R | 220KV GSS University | Shadara | 89213 | 27.02.2025 |  |  | 08:00 | 16:00 | for safety Purpose to carryout Stringing of conductor of 132KV T/Line feed for DESTO due to Construction of Bahara Kahu Over head Road | Shadara
2 | IESCO | Islamaabd | Bahra Kahu | Bahra Kahu (R | 132KV GSS University | Mangial | 122508 | 25.02.2025 |  |  | 08:00 | 16:00 |  | Mangtal
12 | IESCO | Chakwal | Dhudial | Tariq Shaheed | 132KV Chakwal | Sarkal | 2207 | 26.02.2025 | 26.02.2025 |  | 09:00 | 14:00 | for Shifting of HT line 11KV Sarkal feeder crossing over the house of inhabitant of Moh Jhangir (Safety Hazards) | Sarkal
13 | IESCO | Chakwal | Dhudial | Tariq Shaheed | 132KV Chakwal | Al-Rizwal Mill | 2213 |  | Nil |  | 09:00 | 14:00 |  | Al-Rizwal Mill
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rajjar | A.E (T) Sub Division Chakwal | 132KV Chakwal (CWL-9) - C.S Shah (CSS-1) T/Line along with related earth switch |  |  | 28-02-2025 To 01-03-2025 (Daily Basis) |  |  | 08:00 Hrs | 18:00 Hrs | For Energization of Bus Bar of 132KV GSS Dil Jabba (Khan Pur) | No area will be affected as 132KV GSS C.S Shah will be fed from 132KV GSS Chakwal
1 | IESCO | Chakwal | Chakwal | Ghaziabad | Chakwal | MUREED | 2201 | 27.02.2025 |  |  | 10:00 | 13:00 | For Set-righting of tilted HT Structure at District Bar District Complex | District Complex, Chakora, New Chakwal City, Village Mureed, Thoa Bahadar, Hastal, Balkassar Motorway Interchange, Dhoke Maken, Dhoke Sayal, Hastal etc
1 | IESCO | Jhelum | Jhelum-II | Dina-I | Dina | M. Riaz Shaheed | 46808 | 26.02.2025 |  |  | 1000 Hrs | 1300 Hrs | Bifurcation of 11KV Co. M.Akram & Dina City feeders | Chamala, etc